## Slide 1: Squeezer Update Review
February 9, 2010
H1 Squeezer Experiment
ANU, AEI, MIT, CIT and LHO collaboration

## Slide 2: Highlights
New postdoc: Lisa B.
ANU OPO development
  Ready to ship (schedule says March 2010).
  Traveling wave bowtie design works.
  Grad. students will travel to MIT to set it up.
LHO
  RF electronics: built, 50% installed, working.
  TTFSS for laser locking: built, installed, working.
  Demodulator design by Rich A., 1st unit in hand, working.
  Servo board (CM): 2 units built, ready for testing.
  Slow controls (Beckhoff): 1 unit built, working.
  Completion expected: May 2010.
MIT
  Lasers fully operational, locked with 1MHz bandwidth.
  Optics ordered for SHG mirrors, HR mirrors, beam splitters, dichroics.

## Slide 7: ANU Traveling wave OPO

## Slide 8: OPO Performance

## Slide 10: Previously
Grad. students Sheila D. (MIT), Sheon C. (ANU) and Michael S. (ANU)
OPO development at ANU
  6 dB of squeezing observed, traveling wave bowtie design works
AEI loaner SHG at MIT
Noise model and simulation completed
  Showed we can eliminate fiber stabilization
  All network compensation filters are designed
  No show stopper

## Slide 11: Schedule
OPO development at ANU basically completed on schedule
AEI homodyne detector at ANU
Noise model completed
Assembly at MIT
  Lasers, laser locking done
  Optics procurement about ~2 months late
  OPO integration will be about ~2 months late (will start May 2010)
Electronics production at LHO
  About 80% complete, on schedule to complete May 2010

## Slide 12: Plan
Continue to test AEI SHG Built our own when we get the optics
OPO to arrive in May 2010
  OPO integration will start immediately afterwards
Electronics production will wrap up in May 2010
Advanced LIGO Faraday isolator (Mike S.) assembled by June 2010
Need to start thinking about in-vacuum work
Initial funding (210k) is exhausted

## Slide 13: Budget Request
Task | Remainder | FY10: Q3/Q4
Electronics | 55k | 55k
Remote beam alignment | 25k | 0k
Remaining optics (e.g., lenses) | 50k | 50k
OPO super polished optics | 25k | 25k
In-vacuum stuff (excl. Faraday) | 10k | 10k
Travel | 60k | 20k
Total | 225k | 160k
Past request: 210k (all spent and committed by end of January)
Original request: 430k total

## Slide 14: Summary
Lasers and OPO ready
Electronics is nearing completion
No major roadblocks so far
More funding is required now
On budget & on schedule