| Date: | July 21, 2010 |
| --- | --- |
| Refer to: | LIGO-L1000318-v2 |
| Contact: | Stan Whitcomb, stan@ligo.caltech.edu |

Please find on the following pages a concise chronology of events relevant to the design, and construction of the LIGO Observatories and the commissioning and observation with the initial and enhanced detectors.

1970s

1970s	Feasibility studies and early work on laser interferometer gravitational-wave detectors

1979	National Science Foundation (NSF) funds Caltech and MIT for laser interferometer R&D

1980s

1989   December	Construction proposal for LIGO submitted to the NSF

1990s

1990   May	National Science Board approves LIGO construction proposal

1991   March	LIGO project receives 19 site proposals from 17 states

1991   	Caltech 40-meter interferometer operated with LIGO displacement sensitivity

1991   Fall	Congress approves first year funding for LIGO

1992   February	NSF selects LIGO sites: Hanford, Wash., and Livingston, La.

1992   May	LIGO Cooperative Agreement signed by NSF and Caltech

1993   Summer	NSF review panel endorses technical status of LIGO

1993   Summer	Start of LIGO vacuum system engineering design

1993   August	Contract for beam tube design signed

1994   July	Groundbreaking at Hanford site

1994   October	Louisiana site land transfer and leasing agreement executed

1995   July	Groundbreaking at Livingston site

1995   Fall	Contract for vacuum equipment and for vacuum beam tube fabrication signed

1996   Summer	Contracts for construction of buildings and of concrete slab at Hanford site signed

1996   October	Installation of vacuum beam tubes begins at Hanford site

1996   December	Raw glass for mirrors arrives at LIGO

1996   December	Contracts for construction of buildings and beam tube enclosures at Livingston site signed

1997   June	First polished glass arrives at LIGO

1997   July	MIT prototype demonstrates “splitting a fringe” at LIGO sensitivity goal.

1997   August	Buildings at Hanford accepted and occupied by LIGO

1997   August	First of four 10-watt lasers received at LIGO for testing

1997   October	Installation of vacuum beam tubes begins at Livingston site

1997   December	LIGO receives final shipment of raw glass

1998   February	All vacuum beam tube modules at Hanford accepted

1998   May	First completed mirrors arrive at LIGO

1998   September	40-meter interferometer operated with LIGO optical configuration

1998   September	First 10-watt stabilized laser installed at Hanford

1998   September	Installation of seismic isolation system begins at Hanford

1998   October	Buildings at Livingston accepted and occupied by LIGO

1998   October	First beam tube module at Hanford is baked to remove excess water and other chemicals

1998   November	Vacuum system at Hanford accepted by LIGO

1998   November	All vacuum beam tube modules at Livingston accepted by LIGO

1998   December	First fully characterized mirror arrives at Hanford

1999   January	Vacuum system at Livingston accepted by LIGO

1999   February	Installation of seismic isolation system begins at Livingston

1999   May	All beam tube modules at Hanford are baked

1999   June	Coating of mirrors complete

1999   September	First vacuum beam tube module at Livingston completes bake

1999   November	LIGO Inauguration Ceremony

2000s

2000   May	Completed installation of interferometer components for Hanford 2-km interferometer

2000   June	Completed bake of the beam tube(s) at Livingston

2000   October	Achieved “first lock” on Hanford 2-km interferometer in power-cycled configuration

2001   February	Earthquake in Washington State disrupts commissioning

2001   December	E7 Engineering Run, first coincident operation of all three LIGO interferometers 
	plus GEO600 interferometer in Germany and LSU bar detector

2002   August	First scientific operation of all three interferometers in S1 run operating with
	GEO600 and TAMA300 (Japan) interferometers

2003   Feb-Apr	Second science run (S2) with improved sensitivity, operating with TAMA300

2003   Nov-Dec	Third science run (S3) operating with GEO600 and TAMA300 interferometer

2004   Mar-June	Installation of active anti-seismic system at Livingston

2004   	Upper limits papers using S1 data published in Physical Review

2005   November	Design sensitivity reached; begin year long data run (“S5”)

2005-2006   	Improved upper limits using data from S2-S4 published

2007   May	Joint observations start with the French-Italian Virgo instrument

2007   October	Science run of one year integrated quality data at design sensitivity completed (“S5”)

2007-2009   	Initial detectors improved with selected Advanced LIGO technologies (“Enhanced LIGO”)

2008   July   	First scientific paper using S5 data published

2009   July	Science run (“S6”) starts with enhanced initial detectors

2010   October	Science run S6 ends, start of Advanced LIGO installation

# Text boxes

LIGO CALTECH	LIGO MIT

MC 18-34		MIT NW22-295, 185 ALBANY ST

PASADENA CA 91125	CAMBRIDGE MA 02139

TEL: 626.395.2129	TEL: 617.253.4824

FAX: 626.304.9834	FAX: 617.253.7014