## Slide 1: aLIGO Integration status 23 May 2012

## Slide 2: Communication
New email list created for aLIGO integration & commissioning:
aligo_ifo@ligo.org
Sign up: https://grouper.ligo.org/selfmanage/aligoIFO
Biweekly commissioning meetings at LHO:
Mon & Thur, 8.45 am local
Weekly commissioning meetings at LLO:
Mon afternoon

## Slide 3: Integration status at LHO: Buildup to H2OAT
ITMY chamber (BSC8): everything installed and closed up
  Pumping began last week; minimum of 2 weeks before opening GV to tube
  ISI controls commissioning in progress
ETMY chamber (BSC6): still open
  Final suspension measurements & alignment tweaks
  Expect to close up next week
  2 week minimum pumpdown
Start of H2OAT, as marked by sending light down the arm, looks like mid-June

## Slide 4: Integration status at LLO: Buildup to Input Mode Cleaner
HAM3 chamber: everything installed
  HEPI mechanics installed, but not connected
  ISI controls: transfer functions being measured
HAM2 chamber:
  ISI installed
  Nothing on table yet; should start soon
PSL/IO table
  PSL is ready
  IO almost finished; need to route beam into HAM2 (periscope mirrors, tubes, viewports)
In-vacuum IMC locking could start around end-July

## Slide 5: Integration Issue Tracking
Bugzilla installation for issue tracking (J Hanks)
https://services.ligo-wa.caltech.edu/integrationissues/

## Slide 6: What to put in the issue tracker?
Things that are broken and don’t get fixed right away
Hardware modifications that need to get propagated to all instances
Problems that may be neglected if they are only noted in the alog
New feature requests
Not for software bugs – use CDS bugzilla for that
Other suggestions for how to use it are welcome

## Slide 7: Entering Issues
Bugzilla calls them Products, for us they’re the subsystems
Will expand AOS to:
Stray Light Control
Optical Levers
Photon Calibrator
Transmission Monitor

## Slide 8: Entering issues, cont’d
You must enter a Component
aLIGO: issue applies to all interferometers
H1: issue applies to H1 only
L1: issue applies to L1 only
I1: issues applies to I1 only
Other fields are designed for software bug tracking, and can be ignored

## Slide 9: Assignees & Status
Each component, for each product (subsystem), has default assignee names – i.e., email addresses for notification
  Propose that the default assignee, for all components of a subsystem, be the subsystem lead
  Default CC list: subsystem co-lead
Status starts out as ‘NEW’; can be changed to:
  ‘ASSIGNED’ (use to indicate issue is being worked)
  ‘RESOLVED’

## Slide 10: Current issues in the system
Note that search result list does not indicate subsystem (product)
Could add the subsystems as choices for the OS field - ?