## Sheet1
Test Mass Optics: Summary of Location, Type, Method of Suspension, Install Dates
|  | T1200324-v18 |  | v18 updated 7th April 2014
Norna Robertson and Garilynn Billingsley
Site | Interferometer | Chamber | Optic Name | Optic actually used | serial # | pilot or final optic | Method of Suspension | Fiber weld start date or wire hang start date and schedule ID | Cartridge install start date and schedule ID | Comments
LHO | H2 | BSC8 | ITMY | Corning ETM coated as an ITM | ETM02 | pilot | wire, metal prism break-off |  | Dec 2011 (actual) | installed, then removed to BSC1 (see below)
|  | BSC6 | ETMY | Corning ETM coated as an ITM | ETM04 | pilot | monolithic |  | April 2012 (actual) | installed
LHO | H1 | BSC1 | ITMY | Corning ETM coated as an ITM | ETM02 | pilot | wire, metal prism break-off | N/A, see comments | November 2012 (actual) | installed - transferrred from BSC8
|  | BSC1 | ITMY |  | ITM11 | final | monolithic | done | N/A, see comments | Build up new lower stage in LVEA and carry out monolithic assembly before vent and swap. Vent and swap start date is 17 June 2014 (IN-H1-F5116).
|  | BSC3 | ITMX |  | ITM09 | pilot | wire, sapphire prism break-off | done | done | installed
|  | BSC3 | ITMX |  | ITM03 | final | monolithic | done | N/A, see comments | Build up new lower stage in LVEA and carry out monolithic assembly before vent and swap. Vent and swap start date is 3 June 2014 (IN-H1-F3880).
|  | BSC9 | ETMX |  | ETM08 | final | monolithic | done | done | installed
|  | BSC10 | ETMY |  | ETM12 | final | monolithic | done | done | installed
LLO | L1 | BSC1 | ITMY |  | ITM08 | final | monolithic | done | done | installed
|  | BSC3 | ITMX |  | ITM04 | final | monolithic | done | done | installed
|  | BSC4 | ETMX |  | ETM03 | final | monolithic | done | done | installed
|  | BSC5 | ETMY |  | ETM09 | final | monolithic | done | done | installed
Dates from G100061-v52 (April 2014)