## In-air Detectors
Date of last document update | 2014-04-29
Updated by | R. Abbott
D1102418 | Serial Number | Location | Detector Type | Single Supply Fix | Test Status
Single Channel WFS RFPD (24.078 MHz) | S1203264 | LLO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1203265 | LHO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1203014 | LLO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1203015 | LLO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1300267 | LHO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1300268 | LHO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1300514 | CIT | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1300515 | LLO | In-air | Retrofitted | Tested
Single Channel WFS RFPD (24.078 MHz) | S1300516 | LHO | In-air | Retrofitted | Tested
Total Count To Produce | 9
Remaining To Produce | 0
D1101176 | Serial Number | Location | Detector Type | Single Supply Fix | Test Status
LSC Style RFPD (24.078 MHz) | S1202527 | LLO | In-air | Retrofitted | Tested
LSC Style RFPD (24.078 MHz) | S1203396 | LLO | In-air | Retrofitted | Tested
LSC Style RFPD (24.078 MHz) | S1203263 | LHO | In-air | Retrofitted | Tested
LSC Style RFPD (24.078 MHz) | S1203399 | CIT | In-air | Retrofitted | Tested
LSC Style RFPD (24.078 MHz) | S1203397 | LHO | In-air | Retrofitted | Tested
LSC Style RFPD (24.078 MHz) | S1203398 | CIT | In-air | Retrofitted | Tested
Total Count To Produce | 6
Remaining To Produce | 0
D1101176 | Serial Number | Location | Detector Type | Single Supply Fix | Test Status
LSC RFPD ( 9 MHZ and 45 MHz ) | S1203919 | LHO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1203920 | LLO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1203248 | LLO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300520 | LLO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300521 | LHO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300522 | LHO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300523 | LHO | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300524 | CIT | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300525 | CIT | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300526 | CIT | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300527 | CIT | In-air | Retrofitted | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300528 | CIT | In-air | Retrofitted | Tested
Total Count To Produce | 12
Remaining To Produce | 0
D1101176 | Serial Number | Location | Detector Type | Single Supply Fix | Test Status
PSL Style RFPD (21.500MHz) | S1203774 | LLO | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1203775 | LHO | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300535 | AEI | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300536 | CIT | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300537 | CIT | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300538 | LLO | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300539 | LHO | In-air | Retrofitted | Tested
PSL Style RFPD (21.500MHz) | S1300540 | CIT | In-air | Retrofitted | Tested
Total Count To Produce | 8
Remaining To Produce | 0
D1101202 | Serial Number | Location | Detector Type | Single Supply Fix | Test Status
WFS RFPD (9 MHz and 45 MHz) | S1300501 | LLO | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300502 | LHO | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300503 | CIT | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300504 | LHO | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300505 | CIT | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300506 | CIT | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300507 | CIT | In-air | Retrofitted
WFS RFPD (9 MHz and 45 MHz) | S1300508 | CIT | In-air | Retrofitted | Tested
WFS RFPD (9 MHz and 45 MHz) | S1300549 | LLO | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300510 | LLO | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300509 | LLO | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300512 | LHO | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300513 | CIT | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300511 | LHO | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300550 | CIT | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300551 | CIT | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300627 | CIT | In-air | Retrofitted | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300628 | CIT | In-air | Retrofitted | Tested
Total Count To Produce | 18
Remaining To Produce | 1

## In-vacuum Detectors
D1101176 | Serial Number | Location | Detector Type | Detector Usage | Test Status | Welded Shut | Class A
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300529 | LLO | In-vacuum | LSC REFL | Tested | Welded | Done
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300530 | LLO | In-vacuum | LSC POP | Tested | Welded | Done
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300531 | LLO | In-vacuum | Spare | Tested | Welded | Done
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300532 | SRI | In-vacuum | Spare | Tested | In-process
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300533 | LHO | In-vacuum | LSC REFL | Tested | Welded | Done
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300534 | LHO | In-vacuum | LSC POP | Tested | Welded | Done
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300629 | CIT | In-vacuum | Spare | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300630 | CIT | In-vacuum | Spare | Tested
LSC RFPD ( 9 MHZ and 45 MHz ) | S1300631 | CIT | In-vacuum | Spare | Tested
Total Count To Produce | 9
Remaining To Produce | 4
D1101202 | Serial Number | Location | Detector Type | Detector Usage | Test Status | Welded Shut | Class A
WFS RFPD (9 MHz and 45 MHz) | S1301242 | LHO | In-vacuum | ASC-REFL-A | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301243 | LHO | In-vacuum | ASC-REFL-B | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301244 | LLO | In-vacuum | Failed | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301245 | LLO | In-vacuum | ASC-REFL-B | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301246 | LLO | In-vacuum | ASC-REFL-A | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301247 | LLO | In-vacuum | Spare | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301248 | LHO | In-vacuum | Spare | Tested | Welded | Done
WFS RFPD (9 MHz and 45 MHz) | S1301249 | CIT | In-vacuum | Spare | Tested
WFS RFPD (9 MHz and 45 MHz) | S1301250 | CIT | In-vacuum | Spare | Tested
Total Count To Produce | 9
Remaining To Produce | 2
D1101202 | Serial Number | Location | Detector Type | Detector Usage | Test Status | Welded Shut | Class A
WFS RFPD (36 MHz and 45 MHz) | S1300632 | LLO | In-vacuum | ASC-AS-A? | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300633 | LLO | In-vacuum | ASC-AS-B? | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300634 | LHO | In-vacuum | ASC-AS-B | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300635 | LHO | In-vacuum | ASC-AS-A | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300636 | LLO | In-vacuum | Spare? | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300637 | LHO | In-vacuum | Spare | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300638 | CIT | In-vacuum | Spare | Tested | Welded | Done
WFS RFPD (36 MHz and 45 MHz) | S1300639 | CIT | In-vacuum | Spare | Tested
WFS RFPD (36 MHz and 45 MHz) | S1300640 | CIT | In-vacuum | Spare | Tested
Total Count To Produce | 9
Remaining To Produce | 2
? Means I'm not sure