## summary
FABRICATION ACCEPTANCE REVIEW STATUS
Punch List #
Subsys | Pending | Underway | Completed | Total | % complete | closed | open | % complete
AOS | 0 | 1 | 11 | 12 | 91.67% | 171 | 9 | 95% | Pcal, SLC
COC | 0 | 1 | 0 | 1 | 0%
DAQ | 0 | 0 | 1 | 1 | 100% | 18 | 0 | 100%
FMP | 0 | 0 | 3 | 3 | 100% | 0 | 0 | 100%
IO | 0 | 0 | 9 | 9 | 100% | 69 | 50 | 57.98%
ISC | 0 | 3 | 12 | 15 | 80% | 0 | 25 | 0%
PSL | 0 | 0 | 3 | 3 | 100% | 20 | 1 | 95.24%
SEI | 0 | 2 | 51 | 53 | 96.23% | 22 | 55 | 28.57% | BSC-ISI common doc HEPI common doc
SUS | 0 | 0 | 50 | 50 | 100% | 50 | 0 | 100%
Totals | 0 | 7 | 140 | 147 | 95.24% | 350 | 140 | 71.43%
| 0% | 4.762% | 95.24%
2015-03-12
G1300115-v31

## Subsystems
aLIGO Fabrication Acceptance Review Tracking | [6 empty] | G1300115-v21
Review Content
| Pending, Underway, or Completed | Systems Accepted | Punch List Closed | Subsystem | Subassembly | Instance | Acceptance Report (template E1300457) | Acceptance Review Report | Punch List | Resolved punch list # | TBD punch list # | OPS punch list # | Point(s) Of Contact | Comments/Status
| X |  |  | AOS - Video System |  | All | NA | T1200556 | NA |  |  |  | J. Betzwieser | No acceptance document/data yet
| C | A |  | AOS - IAS |  | NA | E1300547 | E1300547 | E1400347 | 23 | 1 |  | D. Cook | Systems review underway
| C | A |  | AOS - OpLev |  |  | E1200026 | T1400232 | L1300227 | 44 | 1 |  | E. Gustafson
| U |  |  | AOS - PCal |  |  | E1400036 | T1400283 | L1400166 |  |  |  | R. Savage | Systems review of PCAL to start in Nov 2014
| C |  |  | AOS - SLC & VP |  |  | E1300212 | T1400233 | E1300806 | 84 | 4 |  | D. Coyne | Under Systems review now
| C | A |  | AOS - TCS | RH | L1, H1, I1 | E1300799 | T1400004 | L1400150 | 0 | 0 |  | A. Brooks | Under Systems review now
| C | A |  | AOS - TCS | HWS | L1, H1, I1 | E1300802 | T1400005 | L1400149 | 0 | 0 |  | A. Brooks | Under Systems review now
| C | A |  | AOS - TCS | CO2P | L1, H1, I1 | E1300892 | T1400006 | L1400148 | 10 | 2 |  | A. Heptonstall | Under Systems review soon
| X |  |  | AOS - TCS |  |  | E1200636
| C | A |  | AOS - TMS |  | L1 EndX | E1300363 | L1300226
| C | A |  | AOS - TMS |  | L1 EndY | E1300362 | L1300226
| C | A |  | AOS - TMS |  | H1 EndX | E1300361 | L1300226
| C | A |  | AOS - TMS |  | H1 EndY | E1300360 | L1300226
| X |  |  | AOS - TMS |  | I1 EndX | TBD | [6 empty] | parts only, no accepted subassembly
| X |  |  | AOS - TMS |  | I1 EndY | TBD | [6 empty] | parts only, no accepted subassembly
| X |  |  | AOS - TMS |  |  | T1400282 | L1300225
| C |  |  | AOS - TMS |  |  | E1300359 | T1400282 | L1300226 | 20 | 3 |  | C. Torrie & E. Gustafson | common document has been mostly completed; documents for individual TMS pending
| X |  |  | AOS | [5 empty] | 171 | 9
| U |  |  | COC | COC | L1, H1, I1 | E1300769 | NA | NA |  |  |  | G. Billingsley, P. Fritschel | Peter has begun to review the COC acceptance documents
| X |  |  | DAQ |  |  |  | T1400534
| C |  |  | DAQ | DAQ | L1, H1 | E1300539 | E1300536 | E1300883 | 18 | 0 |  | R. Bork, D. Barker | Waiting on Systems final acceptance
| X |  |  | DCS |  |  | NA | NA | NA | NA | NA |  | S. Anderson | DCS will be reviewed separately
| C | A |  | FMP | Facility Modifications | L1, H1 | E1300450 | T1300707 | none | 0 | 0 |  | J. Worden | L1 documentation has proved a challenge. Checking docs on high value contracts
| C | A |  | FMP | Tooling | L1, H1, I1 | E1300451 | T1300707 | none | 0 | 0 |  | J. Worden | Going slowly: in some cases, FMP just paid the bill. I'm still looking for a few documents.
| C | A |  | FMP | Software | L1, H1 | E1300452 | T1300707 | none | 0 | 0 |  | J. Worden | Completed documents under review
| X | A |  | FMP |  |  | E1300460 | NA | none | 0 | 0 |  | J. Worden
| C | A |  | IO | IO on PSL Table | L1, H1, I1 | T1300019 | T1300607 | L1400147 | 11 | 0 |  | G. Mueller, M. Heintze | Systems review
| C | A |  | IO | IO in HAM2 | L1, H1, I1 | T1300021 | T1300897 | L1400155 | 8 | 6 |  | G. Mueller, M. Heintze | Systems review
| C | A |  | IO | IO in HAM3 | L1, H1, I1 | T1300022 | T1300896 | L1400156 | 1 | 4 |  | G. Mueller, M. Heintze | Systems review
| C |  |  | IO | IO Tables | L1, H1, I1 | T1300023 | T1300900 | L1400157 | 4 | 4 |  | G. Mueller, M. Heintze | Systems review
| C | A |  | IO | HAM Aux Sus | L1, H1, I1 | T1300020 | T1300680 | L1400158 | 5 | 10 |  | G. Mueller, M. Heintze | waiting on response to Brian O'Reilly's questions, then Systems Review
| C |  |  | IO | EOM | L1, H1, I1 | T1300608 | T1300608 | L1400159 | 5 | 1 |  | G. Mueller, M. Heintze | Systems review
| C |  |  | IO | Power Control | L1, H1, I1 | T1300089 | T1300898 | L1400167 | 2 | 2 |  | G. Mueller, M. Heintze | Matt Heintze reviewing
| C |  |  | IO | IMC | L1, H1, I1 | T1300090 | T1300899 | L1400160 | 1 | 0 |  | G. Mueller, M. Heintze | Systems review
| C |  |  | IO | IFI | L1, H1, I1 | T1300091 | T1300605 | L1400161 | 9 | 3 |  | G. Mueller, M. Heintze | Systems review
| X |  |  | IO | IO Final Design Review actions |  |  |  | L1400173 | 23 | 20
| X |  |  | IO |  |  | E1201013 | E1300793 | see individual lists | 69 | 50 |  | G. Mueller, M. Heintze
| C | A |  | ISC | Custom Optics | L1, H1, I1 | E1300854 | E1300854 | E1400172 | 0 | 1 |  | S. Whitcomb, L. Barsotti
| C | A |  | ISC | RF Sources & Distribution | L1, H1, I1 | E1400081 | E1400081 | E1400172 | 0 | 7 |  | S. Whitcomb, R. Abbott
| C | A |  | ISC | Demodulators & PFDs | L1, H1, I1 | E1300827 | E1300827 | E1400172 | 0 | 5 |  | S. Whitcomb, R. Abbott
| C | A |  | ISC | Signal Conditioning Electronics | L1, H1, I1 | E1300973 | E1300973 | none | 0 | 0 |  | S. Whitcomb, R. Abbott
| C | A |  | ISC | Common Mode Servos & SM Summing | L1, H1, I1 | E1400194 | E1400194 | E1400172 | 0 | 2 |  | S. Whitcomb, P. Fritschel
| C | A |  | ISC | Tip-Tilt Mounts | L1, H1, I1 | E1300878 | E1300878 | E1400172 | 0 | 3 |  | S. Whitcomb, P. Fritschel
| C | A |  | ISC | Beam Diverters | L1, H1, I1 | E1400011 | E1400011 | E1400172 | 0 | 1 |  | S. Whitcomb, R. Abbott
| C | A |  | ISC | Custom Photodetectors | L1, H1, I1 | E1400145 | E1400145 | E1400172 | 0 | 0 |  | S. Whitcomb, P. Fritschel
| C | A |  | ISC | Fast Shutters | L1, H1, I1 | E1500050 | E1500050 | E1400172 | 0 | 0 |  | S. Whitcomb, R. Abbott
| C | A |  | ISC | In-Air Tables | L1, H1, I1 | E1400395 | E1400395 | E1400172 | 0 | 3 |  | S. Whitcomb, P. Fritschel
| C | A |  | ISC | In-Vacuum Tables | L1, H1, I1 | E1400479 | E1400479 | E1400172 | 0 | 3 |  | S. Whitcomb, P. Fritschel
| C | A |  | ISC | Electronics Racks | L1, H1, I1 | E1500003 | E1500003 | E1400172 | 0 | 0 |  | S. Whitcomb, P. Fritschel
| U |  |  | ISC | Arm Length Stabilization (ALS) | L1, H1, I1 | E1500156 | E1500156 | E1400172 |  |  |  | S. Whitcomb, P. Fritschel
| X |  |  | ISC | LSC Real-Time Model | L1, H1, I1 | [6 empty] | S. Whitcomb, P. Fritschel | Decided in the end not to include in the data package
| X |  |  | ISC | ASC Real-Time Model | L1, H1, I1 | [6 empty] | S. Whitcomb, P. Fritschel | Decided in the end not to include in the data package
| U |  |  | ISC | Slow Controls | L1, H1, I1 | E1200305 |  | E1400172 |  |  |  | S. Whitcomb, D. Sigg
| U |  |  | ISC | OMC | L1, H1, I1 |  |  | E1400172
| X |  |  | ISC |  |  | E1300833 | see individual reports | E1400172 | 0 | 25 |  | S. Whitcomb, P. Fritschel
| C | A |  | PSL | NA | L1 | E1200039 | Notes&Changes E1200039 | section 5 of E1100716 | 14 | 0 |  | B. Willke | punch list has been addressed; responses under review
| C | A |  | PSL | NA | H1 | E1200040 | T1400172 | L1400133 | 6 | 1 |  | B. Willke
| C | A |  | PSL | NA | I1 | E1200040 | T1400172 | L1400133 |  |  |  | B. Willke
| X |  |  | PSL |  |  | E1200038 | see individual reports | see individual reports | 20 | 1 |  | B. Willke
| X |  |  | SEI | HEPI | L1 HAM1 | E1200690 | [5 empty] | F. Matichard, C. Torrie, D. Coyne | NO DOCUMENT; DECLARING ACCEPTED BY SIMILARITY
| C |  |  | SEI | HEPI | L1 HAM2 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 HAM3 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 HAM4 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 HAM5 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| X |  |  | SEI | HEPI | L1 HAM6 | E1200690 | [5 empty] | F. Matichard, C. Torrie, D. Coyne | NO DOCUMENT; DECLARING ACCEPTED BY SIMILARITY
| C |  |  | SEI | HEPI | L1 BSC1 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 BSC2 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 BSC3 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C |  |  | SEI | HEPI | L1 BSC4 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| X |  |  | SEI | HEPI | L1 BSC5 | E1200690 | [5 empty] | F. Matichard, C. Torrie, D. Coyne | NO DOCUMENT; DECLARING ACCEPTED BY SIMILARITY
| X |  |  | SEI | HEPI | L1 Corner Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| X |  |  | SEI | HEPI | L1 Xend Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| X |  |  | SEI | HEPI | L1 Yend Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| C | A |  | SEI | HEPI | H1 HAM1 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 HAM2 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 HAM3 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 HAM4 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 HAM5 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 HAM6 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 BSC1 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 BSC2 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 BSC3 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 BSC9 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HEPI | H1 BSC10 | E1200690 | E1200690 |  |  |  |  | F. Matichard, C. Torrie, D. Coyne
| X | A |  | SEI | HEPI | H1 Corner Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| X | A |  | SEI | HEPI | H1 Xend Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| X | A |  | SEI | HEPI | H1 Yend Pump Station | [6 empty] | F. Matichard, C. Torrie, D. Coyne | pump stations covered with chamber instances
| C | A |  | SEI | HEPI | all 3rd IFO units | E1200690 | E1200690 | [5 empty] | all 3rd IFO HEPI units treated together
| X |  |  | SEI | HEPI | I1 HAM Pier Units | [6 empty] | F. Matichard, C. Torrie, D. Coyne
| X |  |  | SEI | HEPI | I1 BSC Pier Units | [6 empty] | F. Matichard, C. Torrie, D. Coyne
| X |  |  | SEI | HEPI | I1 Pump Stations | [6 empty] | F. Matichard, C. Torrie, D. Coyne
| U |  |  | SEI | HEPI | common doc | E1200687 |  |  | 5 | 8 | 22 | F. Matichard, C. Torrie, D. Coyne | most common documentation done; all component tests done
| C | A |  | SEI | HAM ISI | L1 HAM2 | E1400278 | E1400278 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | L1 HAM3 | E1400277 | E1400277 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | L1 HAM4 | E1400268 | E1400268 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | L1 HAM5 | E1400275 | E1400275 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | L1 HAM6 | E1400276 | E1400276 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | H1 HAM2 | E1400281 | E1400281 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | H1 HAM3 | E1400282 | E1400282 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | H1 HAM4 | E1400283 | E1400283 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | H1 HAM5 | E1400284 | E1400284 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | H1 HAM6 | E1400285 | E1400285 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | I1 HAM2 | E1400287 | E1400287 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | I1 HAM3 | E1400287 | E1400287 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | I1 HAM4 | E1400287 | E1400287 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | I1 HAM5 | E1400287 | E1400287 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI | I1 HAM6 | E1400287 | E1400287 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | HAM ISI |  | E1200686 | E1200686 | T1400616 | 9 | 10 | 9 | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | L1 BSC1 | E1500029 | E1500029 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | L1 BSC2 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | L1 BSC3 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | L1 BSC4 | E1500038 | E1500038 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | L1 BSC5 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | H1 BSC1 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | H1 BSC2 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | H1 BSC3 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | H1 BSC9 |  |  | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | H1 BSC10 | E1500030 | E1500030 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | I1 BSC1 | E1500034 | E1500034 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | I1 BSC2 | E1500034 | E1500034 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | I1 BSC3 | E1500034 | E1500034 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | I1 BSC4 | E1500034 | E1500034 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SEI | BSC ISI | I1 BSC5 | E1500034 | E1500034 | T1400616 |  |  |  | F. Matichard, C. Torrie, D. Coyne
| U |  |  | SEI | BSC ISI | common doc | E1200685 | E1200685 | T1400616 | 8 | 37 | 0 | F. Matichard, C. Torrie, D. Coyne | most documentation done; all H1 & L1 test docs done
| X |  |  | SEI |  |  | E1200684 | see individual reports | see individual lists | 22 | 55 | 31 | F. Matichard, C. Torrie, D. Coyne
| C | A |  | SUS | OMC | L1 OMC | E1400034 | E1400034 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | OMC | H1 OMC | E1400055 | E1400055 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | OMC | I1 OMC | E1400158 | E1400158 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | OMC |  | E1201043 | E1201043 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 MC1 | E1400109 | E1400109 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 MC2 | E1201042 | E1201042 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 MC3 | E1400113 | E1400113 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 PRM | E1400114 | E1400114 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 PR2 | E1300513 | E1300513 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 SR2 | E1400117 | E1400117 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | L1 SRM | E1400116 | E1400116 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 MC1 | E1400118 | E1400118 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 MC2 | E1400119 | E1400119 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 MC3 | E1400120 | E1400120 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 PRM | E1400121 | E1400121 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 PR2 | E1400122 | E1400122 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 SR2 | E1400124 | E1400124 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | H1 SRM | E1400123 | E1400123 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 MC1 | E1300514 | E1300514 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 MC2 | E1400125 | E1400125 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 MC3 | E1400126 | E1400126 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 PRM | E1300497 | E1300497 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 PR2 | E1400127 | E1400127 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 SR2 | E1400129 | E1400129 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS | I1 SRM | E1400128 | E1400128 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HSTS |  | E1201040 | E1201040 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | L1 PR3 | E1300836 | E1300836 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | L1 SR3 | E1400115 | E1400115 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | H1 PR3 | E1300844 | E1300844 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | H1 SR3 | E1400161 | E1400161 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | I1 PR3 | E1400159 | E1400159 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | HLTS | I1 SR3 | E1400160 | E1400160 | T1400181 |  |  |  | N. Robertson, C. Torrie
| X |  |  | SUS | HLTS |  | E1201046
| C | A |  | SUS | HLTS |  | E1201041 | E1201041 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | BS | L1 BS | E1300699 | E1300699 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | BS | H1 BS | E1300712 | E1300712 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | BS | I1 BS | E1400157 | E1400157 | T1400181 |  |  |  | N. Robertson, C. Torrie
| X |  |  | SUS | BS |  | E1201045
| C | A |  | SUS | BS |  | E1201039 | E1201039 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | L1 ITMX | E1300916 | E1300916 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | L1 ITMY | E1300917 | E1300917 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | L1 ETMX | E1400080 | E1400080 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | L1 ETMY | E1400131 | E1400131 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | H1 ITMX | E1400146 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | H1 ITMY | E1400147 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | H1 ETMX | E1300908 | E1300908 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C | A |  | SUS | Quad | H1 ETMY | E1300866 | E1300866 | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | I1 #1 | E1400148 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | I1 #2 | E1400149 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | I1 #3 | E1400150 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| C |  |  | SUS | Quad | I1 #4 | E1400151 |  | T1400181 |  |  |  | N. Robertson, C. Torrie
| X |  |  | SUS | Quad |  | E1201044
| C | A |  | SUS | Quad |  | E1201038 | E1201038 | T1400181 |  |  |  | N. Robertson, C. Torrie
| X |  |  | SUS |  |  | E1400019 | see individual reports | T1400181 | 50 | 0 |  | N. Robertson, C. Torrie
| 179 | # entries
| 0 | # blank entries
| 32 | # Not Applicable (X)
| 147 | # reviews
| 0 | # Pending
| 7 | # Underway
| 140 | # Completed
147