## Fabrication Acceptance Review
| Stray Light Control and Viewport Fabrication Acceptance Punch List |  | E1300806
Review Committee Report
NW-Nichole Washington, SS-Scott Shankle, JL-Jeff Lewis, ES- Eduardo Sanchez, CT-Calum Torrie, EG-Eric Gustafson, GM - Gerardo Moreno, DS-David Shoemaker and DC-Dennis Coyne
[6 empty] | Resolved items | 89
| FabAc Rev - Not Stopping COMPLETION |  |  |  |  | Unresolved items | 0
| This item is COMPLETED | Useful Design and Review Information | E1400388
FabAc Rev - Holding up COMPLETION
| Items | Item Details | Action Items | Responsible Person | Evaluted by SS & NW | Evaluated by JL (est. hours right) | Est. labor hrs | not essential to be completed before fab acc rev complete | DC, EG and CIT comments Sept. 2014 | ES & EG Comments Sept. 2014 to March 2015
Arm Cavity Baffle (ACB)
| Final Design Document (FDD) Identified with a DCC number |  | Review the Arm Cavity Baffle FDR report and update if needed | EG and CT |  |  |  | NO | EG reviewed document T1000747 COMPLETED
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date |  | EG and CT |  |  |  | YES | EG reviewed committee report M1100009 One action item one line below COMPLETED
|  | The committee notes that all of the drawings should still be reviewed and signed off by Systems and the Quality Assurance Manufacturing Team (QAME) prior to proceeding. | [5 empty] | YES | COMPLETED
1 | spares list | Spares list missing | Make a spares list | NW and ES | Requires ICS search: There are spare parts, no spare assemblies. Time Includes: ICS search to create list. Not included: ICS uploads, gathering and kitting. |  | 1 | Yes | The SLC sparing analysis E1400244 lists the parts. COMPLETED
2 |  | D1200275: AdLIGO_AOS_ACB-SUSPENSION ASSY, BSC1-BSC3_H1 L1 | Review drawing and update if needed | JL, SS, EG and ES | v3 Marked up |  | 4 | Yes | Markup Acceptabl Red liines OK. COMPLETED
3 |  | D1002277-BSC10 & D1002383-BSC9 SLC 1 HOLE RIGHT ARM CAVITY BAFFLE ASSY | Find and review drawing and update if needed | JL, SS, EG and ES | D1002277-v2: Complete D1002383-v2: v1 Marked up |  | 4 | Yes | Markup Acceptable COMPLETED
4 | Installation plan/procedure(s) | E1100810 Arm Cavity Baffle Installation/De-installation Procedure | Review E1100810 and update if needed | JL, SS and NW | E1100810-v14: Update from BSC8 Need new pictures | Beyond scope of Fabrication Acceptance Review | 4 | Yes | Missing information in reference in 3.1.1, 4.1.1, 5.3.12, 5.5.8, 5.5.9, 6.4.1, 6.5.1, 6.5.2, 8.2.1 and 8.2.2. Reviewed no update required. COMPLETED
5 | Test results | E1300346 Repository for ACB Baffle Test Results | Make sure that all tests that have been made are in the tree. | JL, EG and NW | Requires updating: Blades, magnets, cables, photodetectors, oxidation testing | Beyond scope of Fabrication Acceptance Review | 3 | Yes | E1300346 contains notes on the vendor and LIGO tests including measurements made on a ACB suspension holding a dummy mass. COMPLETED
8 |  | Fritschel--ISC- one-arm test PD results | Find or prepare a report on the PD from the one arm test. | T. Vo |  |  |  | Yes | PD was used to align arm successfully in one arm test. Collection of test results see T1400463. COMPLETED
Manifold/Cryopump and Mode Cleaner Tube Baffles
| Final Design Document (FDD) Identified with a DCC number |  | Review the Manifold Cryopump and mode cleaner baffle FDR report and update if needed | EG and CT |  |  |  | NO | EG reviewed document T1100165 COMPLETED
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date |  | EG and CT |  |  |  | YES | EG reviewed committee report M1200070 action items remain. They have been turned intoseveral punch List Items and will be resolved. COMPLETED
10 | parts list (BOM) | D1003181 aLIGO_Manifold Cryo Baffle_Assembly, ETMX H1 | Review the BOM on D1003181 and Update if needed | NW, SS and ES | D1003181-v4 needs correction |  | 2 | Yes | ES reviewed and it is up to date. COMPLETED
11 |  | D1003228 aLIGO_Manifold Cryo Baffle_Assembly, ETMY H1 | Review the BOM on D1003228 and update if needed | NW, SS and ES | D1003228-v4 needs correction |  | 2 | Yes | ES reviewed and it is up to date. COMPLETED
12 | spares list |  | Make a spares list | NW and ES | Requires ICS search: There are spare parts, no spare assemblies. Time Includes: ICS search to create list. Not included: ICS uploads, gathering and kitting. |  | 1 | Yes | The SLC sparing analysis E1400244 lists the parts. COMPLETED.
13 | design drawings, schematics, interfaces, etc. | E1300352 Repository for Manifold/Cryopump & Mode Cleaner Tube Baffle Design Drawings, Interfaces, etc. | Review E1300352 and update if needed | JL, SS, EG and ES | E1300352: Placeholder with no MC Tube Baffle info |  | N/A | Not Relevant | Information in related documents - COMPLETED
14 |  | E1100718 Mode Cleaner Tube Baffle Assembly and Installation Procedure | Review E1100718 and update if needed | JL, SS, EG and ES | E1300718 / D1000774 need tube location information. |  | 2 | Yes | Reviewed by Systems and update not required. COMPLETED
17 | Test results | E1300423 Repository for Manifold/Cryo Baffle Test Results | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | Requires updating: Blades, magnets, oxidation testing: May require MCT Repository | Beyond scope of Fabrication Acceptance Review | 3 | Yes | E1300423 contains installation data and LIGO tests including B&K hammer tests, ring down tests and vertical and longitudinal transmissability measurememnts. COMPLETED
Beam Splitter Elliptical Baffle
| Final Design Document (FDD) Identified with a DCC number | [6 empty] | NO | EG and CT found and reviewed document T1200313. COMPLETED
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date |  | EG and CT |  |  |  | YES | EG and CT found RODA M1200268. DS Accepts COMPLETED
18 | prototype tests | Calum | Find the report on prototype tests and enter it in the DCC | JL, EG and NW | Requires Calum's input: No postings in E1300426 |  | 1 | Yes | No Testing completed past time when it can be done. COMPLETED
19 | drawing/document tree/list |  | Update the document tree list if needed | JL, EG, ES |  | Need to add files to the doc tree (repository) E1300355 | 1 | Yes | ES asked to review on 15 March 2015. On March 17, 2015 ES confirmed that the Document Tree has no issues. COMPLETED
20 | spares list |  | Make a spares list | NW and ES | No spare parts or assemblies |  | N/A | Yes | The SLC sparing analysis E1400244 lists the parts. COMPLETED.
21 | design drawings, schematics, interfaces, etc. | E1300355 Repository for BS Elliptical Baffle Design Drawings, Interfaces, etc. | Review E1300355 and update if needed | JL, SS, EG and ES | Placeholder only |  | N/A |  | Drawings reviewed by ES and EG. they are current. COMPLETED
22 |  | D1200750: aLIGO, AOS, BS ELLIPTICAL BAFFLE ASSY | Review D1200750 and update if needed | JL, SS, EG and ES | D1200750 - Reviewed by ES and EG and up to date. | COMPLETED
23 | Assembly procedure(s) | E1200660 AOS SLC BS Elliptical Baffle Installation Procedure | Review E1200660 and update if needed | NW, SS, JL and EG | See above | COMPLETED
24 | Installation plan/procedure(s) | E1200660 AOS SLC BS Elliptical Baffle Installation Procedure | Review E1200660 and update if needed | NW, SS, JL and EG | Check BS target design |  | 8 | Yes | EG Reviewed. COMPLETED
25 | Safety Docs | E1200659 SLC BS Elliptical Baffle Install Hazard Analysis | Have the Hazard analysis reviewed and signed | EG and NW | Requires approval | Looks to be complete - just needs all approvals | 1 | NO | Documents signed off COMPLETED
28 | Test results | E1300426 Repository for BS Elliptical Baffle Test Results | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | May require updating: Only install tests posted | Beyond scope of Fabrication Acceptance Review | 1 | Yes | No data was entered into the Test forms for this nonsuspended baffle.COMPLETED
ITM Elliptical Baffle
| Final Design Document (FDD) Identified with a DCC number | [6 empty] | NO | EG and CT found and Reviewed document T1100446. COMPLETED
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date. Three items below must be dealt with |  | EG and CT |  |  |  | YES | EG and CT found and reviewed Review Report M1200336 and there are three questions listed below.
|  | Re-design (retrofit) of connection between suspended stage and baffle (box), see LIGO- M1200255. | [6 empty] | Parts are now now installed. Missed opportiunity to redesign. COMPLETED
|  | Map of resonances, see below for more information. At CIT the ITM Elliptical baffle will be re- suspended with final layout. All of the rigid body frequencies should be measured along with the transfer function in the longitudinal direction only. | [6 empty] | All parts now installed. Missed opportiunity to make measurements. COMPLETED.
|  | Interface to stage 0 (dog clamps, tooling fixtures and associated holes), see LIGO-M1200255 | [6 empty] | Parts now installed. Missed opportiunity. COMPLETED.
29 | prototype tests | T1200419 ITM Ellipical Baffle (ITM_EB) First Article Longitudinal Transmissibility with Damper | Is this the complete document on prototype tests? | JL, EG and NW | T1300325? Confirm with Calum |  | 1 |  | This is the only document on Prototype testing. COMPLETED
30 | spares list |  | Make a spares list | NW and ES | Requires ICS search: There are spare parts, no spare assemblies. Time Includes: ICS search to create list. Not included: ICS uploads, gathering and kitting. |  | 4 | The SLC sparing analysis E1400244 lists the parts. COMPLETED.
31 | design drawings, schematics, interfaces, etc. | E1300354 Repository for ITM Elliptical Baffle Design Drawings, Interfaces, etc. | Review E1300354 and update if needed | JL, SS, EG and ES | Placeholder only | Some more docs could be added to this. | 1 |  | ES and EG will Review. | Reviewed and some drawings Red Lined but acceptabe - COMPLETED
32 |  | D0900428 aLIGO Systems, LBSC2-L1 Top Level Chamber Assembly | Review D0900428 and update if needed | JL, SS, EG and ES | COMPLETED
33 |  | D1003238-v5: aLIGO AOS ITM ELLIPTICAL BAFFLE FINAL ASSY H1/L1 | ReviewD1003238 and update if needed | JL, SS, EG and ES | COMPLETED
34 |  | D1101806: aLIGO ITM ELLIPTICAL BAFFLE ASSEMBLY | Review D1101806 and update if needed | JL, SS, EG and ES | COMPLETED
35 |  | D1101885: aLIGO AOS ITM ELLIPTICAL BAFFLE SUSPENSION ASSY | Review D1101885 and update if needed | JL, SS, EG and ES | v3 Marked up |  | 4 | Yes | Markup Acceptable COMPLETED | Red Lines OK - COMPLETED
36 | Assembly procedure(s) | E1200677 ITM Elliptical Baffle Assembly Procedure | Review E1200677 and update if needed | NW, SS, JL and EG | COMPLETED
37 | Installation plan/procedure(s) | E1101021 ITM Elliptical Baffle Installation Procedure | Review E1101021 and update if needed | NW, SS, JL and EG | Possible updates pending | Beyond scope of Fabrication Acceptance Review | 4 | Yes | Will be done in installation acceptance review | Reviewed. Basically okay. COMPLETED
38 | Test & Commissioning Doc Tree |  | Make sure that all tests that have been made are in the tree. | JL, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | These are all of the test documents on the ITMN Elliptical Baffle and they are in the tree. COMPLETED
E1300405 Install ITM Elliptical Baffle LHO BSC2 X&Y Test
E1300381 Install ITM Elliptical Baffle LLO BSC2 X&Y Test
E1300427 Repository for ITM Elliptical Baffle Test Results
E1300382 Install ITM Elliptical Baffle LLO BSC2Y Test.
42 | Test results | E1300427 Repository for ITM Elliptical Baffle Test Results | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | Requires updating: Blades, magnets, oxidation testing | Beyond scope of Fabrication Acceptance Review | 1 | Yes | E1300427 contains LIGO tests including a longitudinal transmissibility measurement of a first article with a damper. COMPLETED
Output Faraday Isolator (OFI)
| Final Design Document (FDD) Identified with a DCC number | [6 empty] | NO | EG and CT found and rteviewed document T1000181 COMPLETED
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date |  | EG and CT |  |  |  | YES | EG and CT found and reviewed document L1000319 Design found NOT complete | L1500047 has a discussion of which Punch List items are resolved and which will go into the Operations Bug List. COMPLETED
43 |  | T1300414 Output Faraday Isolator Blade Creep | Did it meet spec.? | JL, CT and EG |  | We don't measure the creep, so N/A |  |  | COMPLETED
44 | prototype tests | OFI Vibration Test Report | report if tested | JL, CT and EG |  | Don't know if there were vib tests done at CIT on the proto. I sent an email to Stuart to ask if the LLO OFI was "hammered" - though those results are beyond the scope of Fab. |  | Yes | All OFIs are installed so this is a missed opportunity. Commissioning will not be interupted to do this measurement. COMPLETED
45 | drawing/document tree/list |  | Update if needed | NW | JL ? | Assuming the E1300351 Repository is the Doc Tree, then there is some more work to be done. | 2 |  | ES and EG will Review. | Reviewed and acceptable - COMPLETED
46 | design drawings, schematics, interfaces, etc. | E1300351 Repository for OFI Design Drawings, Interfaces, etc. | Review E1300351 and update if needed | JL, SS, EG and ES | Placeholder only |  | N/A | YES | Documents reviewed COMPLETED
47 |  | D0900136-v5_AdLIGO_AOS_Faraday Isolator Assembly (HR).PDF | Review D0900136 and update if needed | JL, SS, EG and ES | COMPLETED
48 |  | D0900048: Faraday Isolator Damper Holder Assembly | Review D0900048 and update if needed | JL, SS, EG and ES | COMPLETED
49 |  | D0900170: Faraday Isolator Earthquake Crossbar Assembly | Review D0900170 and update if needed | JL, SS, EG and ES | COMPLETED
50 |  | D0900566: Faraday Isolator Upper Blade Clamp Top | Review D0900566 and update if needed | JL, SS, EG and ES | COMPLETED
51 |  | D0900579: Faraday Isolator Blade Guard Assy | Review D0900579 and update if needed | JL, SS, EG and ES | COMPLETED
52 |  | D0900586: Faraday Isolator Up Wire Assembly | Review D0900586 and update if needed | JL, SS, EG and ES | COMPLETED
53 |  | D0900623: Faraday Isolator Table Assembly | Review D0900235 and update if needed | JL, SS, EG and ES | COMPLETED Assembly Solid works drawings does not match the as built OFI Weight. |  |  |  | ES asked to check drawing on 15 March. ES Confirmed on March 17, 2015 that the document was up to date. COMPLETED
54 |  | D0900655: Structural Weldment Assembly (OMCS) | Review D0900655 and update if needed | JL, SS, EG and ES | COMPLETED
55 |  | D0901514: Faraday Isolator Blade Clamp Platform | Review D0901514 and update if needed | JL, SS, EG and ES | COMPLETED
56 |  | D0902845: Faraday Isolator Refl Baffle | Review D0902845 and update if needed | JL, SS, EG and ES | COMPLETED
57 |  | D1002256: AdLIGO_AOS_D0900136_Earthquake Crossbar-In Assy | Review D1002256 and update if needed | JL, SS, EG and ES | COMPLETED
58 | Test & Commissioning Doc Tree |  | Make sure that all tests that have been made are in the tree. | JL, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Tests for OFI are in L1400233. COMPLETED
59 | Test plan/procedure(s) | T1000192 Output Faraday Isolator Test Plan | Where are the test results for the last two items particularly the wavefront distortion test? | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Tests for H1 OFI are in E1300390, L1 OFI tests are in E1300389 and I1 OFI tests are in E1400294. COMPLETED
| OFI Testing | No test results for third IFO Output Faraday isolator. |  |  |  | G. Moreno & P. King working on 3 rd IFO OFI test report. DCC Number will E1400294. |  |  | E1300428 is the repository for OFI testing and contains the test data on the 3 rd OFI including extinction ratio measurements and Hartmann wavefront measurements in E1400436. When GM finishes extinction measurement this will be done. | Sent email to GM on March 23, 2015 reminding him. Email received from GM on March 24, 2015 saying he was making the additions to the Testing Document. COMPLETED
60 | Safety Docs | E1300283 OFI Assembly & Installation Hazard Analysis | Get hazard analysis completed and signed | EG and NW |  |  |  | NO | Document signed off COMPLETED
63 | Test results | E1300428 Repository for Output Faraday Isolator Test Results | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
64 |  | E1300043 OFI Balance Weights and Locations New Blade Weight Test & analysis | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Added document name to this spreadsheet and to E1300351 Repository
65 |  | T1300342-v1 OFI Optical test results_LLO | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
66 |  | T1300346-v1_OFI Vendor Test Results_Brewster Polarizer | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
67 |  | T1300347-v1_OFI Vendor Test Results_Faraday Rotator | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
68 |  | T1300419 OFI 1st Article Data_hanford iLog | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
69 |  | E1300389 Align/Install Output Faraday Isolator LLO Test | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
70 |  | E1300390 Align/Install Output Faraday Isolator LHO Test | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | JL ? | Beyond scope of Fabrication Acceptance Review |  | Yes | Will be done in installation acceptance review | Reviewed COMPLETED
Signal Recycling Cavity Baffles
| Final Design Document (FDD) Identified with a DCC number | [6 empty] | NO | EG and CT will review document | T1100445
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date. Three items below must be dealt with |  | EG and CT |  |  |  | YES | EG and CT will reviewed Report M1200073 and found the following 4 action items.
|  | Completing the integration of the *new* cut-down SR2 scraper baffle with the table extension and TCS components - from a layout perspective. (The open item is primarily the extension table.) | [6 empty] | refer to LIGO-D0900421-v9 | completed
|  | Confirming all of the holes in the SR2 scraper baffle match the optical layout including the TCS components. (This is done and will be approved via RODA.) | [6 empty] | refer to LIGO-D0900421-v9 | completed
|  | The committee notes that in HAM5 there is now only a SRM AR Baffle. The committee also notes that as a result of the change to the position of SRM, the footprint of the SRM AR baffle will be accommodated by moving the OFI 2 inches in the –Y direction. This is still being checked at the time of writing. | [6 empty] | refer to LIGO-D0900456-v13 | completed
|  | Completing the FEA of the *new* SR2 scraper baffle, this should be in parallel to the purchase. This last item is a systems action. (SR2 scraper baffle is ready and again waiting for integration with table extension.) | [6 empty] | refer to T1200121 | completed.
71 | Assembly procedure(s) | T1300340 SLC Signal Recycling Cavity Baffles Assembly and Installation | Review T1300340 and update if needed | JL, SS, EG and ES | Placeholder only |  | N/A | NO | ES and EFG Reviewed and found no problems. COMPLETED
72 | Installation plan/procedure(s) | E1100784 Initial Alignment Procedure -LHAM4 and LHAM5 | Review E1100784 and update if needed | JL, SS and EG | Not qualified to review |  | ?
73 |  | D0900456 aLIGO Systems, HAM5-L1 Top Level Chamber Assembly | Review D0900456 and update if needed | JL, SS, EG and ES |  |  | 0 |  | ES and EG will Review. | Reviewed and acceptable - COMPLETED
74 | Test results | E1300338 Repository for Signal Recycling Cavity Baffles Test Results | Make sure that all tests that have been made are in the tree. | JL, CT, EG and NW | Appears Complete: Confirm with Calum |  | 0 |  | Changed from D to E document. | Reviwed respsitory E1300338 and it contains laser vibraometry and modal data and some FEA results. COMPLETED
Viewports
75 | Final Design Document (FDD) Identified with a DCC number | T1000746-v7_Viewports_Subsystem_FDD | Review the Viewports FDD and update if needed | DC and NW | Requires updated to fig 34 |  | 1 | NO | EG and CT reviewed document T1000746 COMPLETED | T1000746
| FDD Review Committee Report identified and have a DCC number | Have all of the questions in the FDD Review been answered and is the FDD up to date |  | EG and CT |  |  |  | YES | EG and CT found no review Report | Testing results listed below show that the aLIGO Viewports meet their requirements. COMPLETED
E1101226 Proof test levels for aLIGO Viewports
E1300447 Test-VP LHO
T1200553 Viewport Measurement Report
T1300531 Wedge viewport 500ppm AR Coating Measurement.
E1300438 Repository for Viewport Test Results.
76 | spares list |  | Make a spares list | NW and DC | Requires ICS search: There are spare parts, no spare assemblies. Time Includes: ICS search to create list. Not included: ICS uploads, gathering and kitting. |  | 8 | Yes | The SLC sparing analysis E1400244 lists the parts. COMPLETED.
77 | design drawings, schematics, interfaces, etc. | E1300349 Repository for Viewports Design Drawings, Interfaces, etc. | Review E1300351 and update if needed | DC, SS, EG and ES | Placeholder only |  | N/A |  | ES and EG will Review. | Reviewed and acceptable - COMPLETED
78 |  |  | Can commercial drawings be added? |  |  | Yes but the viewable permission must be set to LIGO lab and a note added that it should never be made public. COMPLETED | 1 |  |  | Email to ES on March 15, 2015 to make sure all the drawings we have of commercial viewports are in the DCC and all have viewing permission set to LIGO Lab. Response on March 17, 2015 from ES saying that all of the commercial drawings were in the DCC and only LIGO Lab viewable. COMPLETED
79 | Test results | E1300438 Repository for Viewport Test Results | Make sure that all tests that have been made are in the tree. | DC, NW, and EG | Requires update: Scratch & Dig, Reflectance Measurements, Proof & Helium Leak Testing |  | 3 | Yes | Will be done in installation acceptance review | Test repository E1300438 contains a pointer to the ICS JIRA record for LHO viewport testing, a spreadsheet showing the status of LLO viewports, a Safety Bulletin on Kovar-sealed glass vacuum viewports, a report on viewport measurements and measurements of the reflectivity of 2 sample wedged viewports. COMPLETED
80 |  | E1300447 TEST-VP | Make sure that all tests that have been made are in the tree. | DC, NW, and EG |  |  |  | Yes | Will be done in installation acceptance review | Review and this document is contained in E1300438. COMPLETED
81 |  | Leak Test & Overpressure Test document | Make sure that all tests that have been made are in the tree. | DC, NW, and EG |  |  |  | Yes | Will be done in installation acceptance review
ISC and Inventory
82 | ICS inventory |  | Update ICS if needed | NW | Requires assemblies |  | 8 | YES | NW and EG reviewed and found 225 Assemblies and subassemblies in ISC Pointer to the right. COMPLETED | Pointer
83 | S-numbers |  | Update S-Numbers if needed | NW | No S-numbers |  | N/A | YES | NW and EG will review. | No updated needed. Completed.