## aLIGO waiver log
aLIGO Waiver Log
waiver type
Request DCC# | approved | rejected | Disposition DCC# | Subsystem | performance/ specification | process/procedure | vacuum/contamination | defect/ deviation | Description (title)
L080101 |  | 1 | L080102 | SYS |  | 1 | 1 |  | Request to relax the stipulation to use fully synthetic machining fluids when requesting parts with small surface area
L0900058 |  | 1 | L1000022 | SUS |  |  | 1 |  | Request for waiver on glass shot blasted parts (BS/FM stay brackets)
L0900066 | 1 |  | L1000178 | SEI |  |  | 1 |  | Request for waiver on Viton material certification and restricted source for a small quantity of small o-rings
L1000343 | 1 |  | L1000346 | SYS |  |  | 1 |  | waiver request - vibratory tumbling for deburring (for mirror mounts)
L1000370 |  | 1 | L1000375 | SEI |  |  | 1 |  | waiver request for press-fit repairs to holes in machined aluminum parts of the HAM-ISI
L1100046 | 1 |  | L1200067 | SYS |  |  | 1 |  | waiver vacuum baking of optics
L1100162 | 1 |  |  | SUS |  |  | 1 |  | VRB question: acceptable to not vacuum bake the CP and ERM to ESD flex connector bond?
C1102498 | 1 |  | C1102498 | VAC |  |  | 1 |  | Waiver to GNB re mid-station spool. FTIR baseline too high.
C1102502 | 1 |  | C1102502 | VAC |  |  |  | 1 | Waiver to GNB re MSS 1 Flange marks.
E1000610 | 1 |  | E1000610 | SEI |  |  | 1 |  | Waiver for the use of Ecocool AP-71 machining fluid for the sealing flange of the SEI storage containers
E1201079 | 1 |  | E1201079 | SEI |  |  | 1 |  | Machining Fluid Waiver Granted for SRI
E1400330 | 1 |  | E1400330 | ISC |  |  | 1 |  | Waiver for another RGA scan of the OMC Breadboard Assy, ASSY-D1201439
E1500061 | 1 |  | E1500055 | COC | 1 |  |  |  | BS01 AR absorption waiver
E1500062 | 1 |  | E1500055 | COC | 1 |  |  |  | BS02 AR absorption waiver
E1500063 | 1 |  | E1500055 | COC | 1 |  |  |  | BS03 AR absorption waiver
E1500064 | 1 |  | E1500055 | COC | 1 |  |  |  | BS04 AR absorption waiver
E1500065 | 1 |  | C1101807 | COC |  |  |  | 1 | BS03 polish waiver
E1500066 | 1 |  | C1103274 | COC |  |  |  | 1 | BS04 polish waiver
E1500067 | 1 |  | C1101973 | COC |  |  |  | 1 | BS05 polish waiver
E1500068 | 1 |  | E1500055 | COC | 1 |  |  |  | BS06 Absorption waiver
E1500069 | 1 |  | E1500055 | COC | 1 |  |  |  | CP09 absorption waiver
E1500070 | 1 |  | C1002059 | COC |  |  |  | 1 | ETM03 polish waiver
E1500071 | 1 |  | bug 614 waiver | COC | 1 |  |  |  | ETM07 Coating, 532 nm reflection waiver
E1500072 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM07 Coating, spherical aberration waiver
E1500073 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM07 Coating, ripple waiver
E1500074 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM08 Coating, ripple waiver
E1500075 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM09 Coating, ripple waiver
E1500076 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM10 Coating, ripple waiver
E1500077 | 1 |  | T1400717 | COC | 1 |  |  |  | ETM11 Coating, ripple waiver
E1500078 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM12 Coating, ripple waiver
E1500079 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM13 Coating, ripple waiver
E1500080 | 1 |  | T1400717 | COC | 1 |  |  |  | ETM14 Coating, ripple waiver
E1500081 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM15 Coating, ripple waiver
E1500082 | 1 |  | T1300354 | COC | 1 |  |  |  | ETM16 Coating, ripple waiver
E1500083 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM01 Coating, ripple waiver
E1500084 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM03 Coating, ripple waiver
E1500085 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM05 Coating, ripple waiver
E1500086 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM06 Coating, ripple waiver
E1500087 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM07 Coating, ripple waiver
E1500088 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM09 Coating, ripple waiver
E1500089 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM10 Coating, ripple waiver
E1500091 | 1 |  | T1300354 | COC | 1 |  |  |  | ITM11 Coating, ripple waiver
E1500092 | 1 |  | T1400252 | COC |  |  |  | 1 | ITM06 Coating, Haze on AR surface
E1500093 | 1 |  | E1500093 | COC |  |  |  | 1 | ITM09 Coating, Haze on AR surface, waiver
E1500094 | 1 |  | E1500094 | COC |  |  |  | 1 | ITM09, Mounting flat fracture, waiver
E1500095 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM08 Coating, spherical aberration waiver
E1500096 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM09 Coating, spherical aberration waiver
E1500097 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM12 Coating, spherical aberration waiver
E1500098 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM11 Coating, spherical aberration waiver
E1500099 | 1 |  | G1100466 | COC | 1 |  |  |  | ETM14 Coating, spherical aberration waiver
E1500100 | 1 |  | T1200295 | COC | 1 |  |  |  | ITM04 Coating, spherical aberration waiver
E1500101 | 1 |  | T1200295 | COC | 1 |  |  |  | ITM08 Coating, spherical aberration waiver
E1500102 | 1 |  | bug 614 waiver | COC | 1 |  |  |  | ETM08 Coating, 532 nm reflection waiver.
E1500103 | 1 |  | bug 614 waiver | COC | 1 |  |  |  | ETM09 Coating, 532 nm reflection waiver.
E1500104 | 1 |  | bug 614 waiver | COC | 1 |  |  |  | ETM12 Coating, 532 nm reflection waiver.
E1500105 | 1 |  | C1204263 | COC |  |  |  | 1 | ETM12 Polish waiver
E1500106 | 1 |  | C1204263 | COC |  |  |  | 1 | ETM13 Polish waiver
E1500107 | 1 |  | C1203264 | COC |  |  |  | 1 | ETM11 Polish waiver, Barrel scuff
E1500108 | 1 |  | C1205170 | COC |  |  |  | 1 | ETM14 Polish waiver, excess defects
E1500109 | 1 |  | C1103158 | COC |  |  |  | 1 | ITM01 Polish waiver, excess defects
E1500110 | 1 |  | C1101807 | COC |  |  |  | 1 | ITM03 Polish waiver, excess defects
E1500111 | 1 |  | C1002863 | COC |  |  |  | 1 | ITM05 Polish waiver, excess defects
E1500112 | 1 |  | C1000386 | COC |  |  |  | 1 | ITM06 Polish waiver, Bevel Defect
E1500113 | 1 |  | C1102248 | COC |  |  |  | 1 | ITM11 Polish waiver, sleek
E1500114 | 1 |  | C1000357 | COC |  |  |  | 1 | PR303 Polish Defect waiver
E1500115 | 1 |  | C1000619 | COC |  |  |  | 1 | SR301 Polish Defect side and bevel fracture, waiver
E1500116 | 1 |  | C1000616 | COC |  |  |  | 1 | SR301 Polish Defect Incorrect arrow and serial number placement, waiver
E1500117 | 1 |  | C1000616 | COC |  |  |  | 1 | SR302 Polish Defect Incorrect arrow and serial number placement, waiver
E1500118 | 1 |  | C1000619 | COC |  |  |  | 1 | SR302 Polish Defect side and bevel fracture, waiver
E1500124 | 1 |  | E1500122 | COC | 1 |  |  |  | ETM08 ETM AR coating waiver
E1500125 | 1 |  | E1500122 | COC | 1 |  |  |  | ETM12 ETM AR coating waiver
E1500126 | 1 |  | bug 4 waiver | COC | 1 |  |  |  | ITM09 AR coating waiver
E1500127 | 1 |  | bug 4 waiver | COC | 1 |  |  |  | ITM03 AR coating waiver
E1500128 | 1 |  | bug 4 waiver | COC | 1 |  |  |  | ITM11 AR coating waiver
E1500129 | 1 |  | bug 4 waiver | COC | 1 |  |  |  | ITM04 AR coating waiver
E1500130 | 1 |  | bug 4 waiver | COC | 1 |  |  |  | ITM08 AR coating waiver
E1500131 | 1 |  | E1500121 | COC |  |  |  | 1 | ETM08 HR coating pinhole, waiver
E1500132 | 1 |  | E1500121 | COC |  |  |  | 1 | ETM09 HR coating pinhole, waiver
E1500149 | 1 |  | T1000154 | COC |  |  |  | 1 | ETM11 HR coating pinhole, waiver
E1500123 |  |  |  | IO |  | 1 |  |  | Fabrication Acceptance Review Status of Input Optics EOM Testing, Modeling and Discussion of need for Waivers from Systems
L1300049 | 1 |  | L1300049 | SYS |  | 1 | 1 |  | Wiha (Hex) Allen Keys - waiver on bake
L1100280 | 1 |  | L1100280 | TMS |  | 1 | 1 |  | Exceptions for NTE re: RFQ A0-301, quote response
Q1100071 | 1 |  | Q1100071 | SUS |  |  |  | 1 | D020023 HSTS Structure Deviation Requests
Q1500001 | 1 |  | Q1500001 | SLC |  | 1 | 1 |  | Waiver: Class B cleaning of 3 Alu parts for the SLC Elliptical Baffle
Q1500002 | 1 |  | Q1500002 | SUS |  | 1 | 1 |  | Waiver: no bake for the H1 SR3 magnet repair
Q1500003 | 1 |  | Q1500003 | SUS |  | 1 | 1 |  | Waiver: EP30 heat cure waiver for L1 SR3
Q1500004 | 1 |  | Q1500004 | SUS |  | 1 | 1 |  | Waiver: to roughen surface of HLTS pen mass in situ
Q1500005 | 1 |  | Q1500005 | SEI |  |  |  | 1 | Waiver: Arland Tool keensert repair proposal
Q1500006 | 1 |  | Q1500006 | SUS |  | 1 | 1 |  | Waiver: no elevated temperature bake of adhesive for PR3 IM
L070089 | 1 |  | L070091 | IO |  | 1 | 1 |  | Request for advice/waivers on some Input Optics elements
Q1500007 | 1 |  | Q1500007 | VAC |  | 1 | 1 |  | Waiver: Class A Waiver Request for 6 blanks at LLO
Q1500008 | 1 |  | Q1500008 | SUS |  | 1 | 1 |  | Waiver Request from Suspensions - room temp out-gassing cure of EP-30-2 on ITM-Y only
Q1500009 | 1 |  | Q1500009 | SUS |  | 1 | 1 |  | Waiver: class B cleaning of AOSEM positioning brackets for the L1 PR3 SUS assembly
Q1500010 | 1 |  | Q1500010 | SUS |  | 1 | 1 |  | Waiver: H1 PR2 AR magnet repair without elevated temperature cure
Q1500011 | 1 |  | Q1500011 | SUS |  | 1 |  |  | Waiver: no impulse response, dynamic testing of the L1 BS with Elliptical Baffle
Q1500012 | 1 |  | Q1500012 | ISC |  | 1 |  |  | Waiver: unapproved source and no material certs for some small Viton o-rings
Q1500013 | 1 |  | Q1500013 | TMS |  | 1 | 1 |  | Waiver: dry machine, no clean and bake, 2 clamps for TMS
Q1500014 | 1 |  | Q1500014 | SUS |  | 1 | 1 |  | Waiver for SmCo magnet/Al jacket assembly
E070288 | 1 |  | L070097 | IO |  | 1 | 1 |  | request for variance on vacuum procedure for IO supermirrors (request for vacuum waiver)
M070383 | 1 |  | M070383 | ISC |  | 1 | 1 |  | cleaning waiver for ELI L1, 2" REO beamsplitter in HAM4
Q1500015 |  | 1 | Q1500015 | VP |  | 1 | 1 |  | Cleaning Procedure Waiver Request for AR Coated and Uncoated Viewports
Q1500016 |  | 1 | Q1500016 | VAC |  | 1 | 1 |  | Need waiver for Al in SS
Q1500017 |  | 1 | Q1500017 | SEI |  | 1 | 1 |  | Need waiver for large parts
Q1500018 | 1 |  | Q1500018 | SEI |  | 1 | 1 |  | Waiver: air bake 4 dowel pins for HAM-ISI actuator assy
Q1500019 | 1 |  | Q1500019 | SEI |  | 1 | 1 |  | Waiver: air bake 50 barrel nuts
Q1500020 | 1 |  | Q1500020 | ISC |  | 1 | 1 |  | Waiver: optics cleaning
Q1500021 | 1 |  | Q1500021 | ISC |  | 1 | 1 |  | Waiver: DLC mount cleaning
bug 20 waiver | 1 |  | L1200291 | SYS | 1 |  |  | 1 | L1 Cpy ESD is inoperative
bug 46 waiver | 1 |  | E1201105 | IO |  |  |  | 1 | Reversal of wedge orientation for hanging PR3-01 in H1
bug 195 waiver | 1 |  | T1300632 | SYS |  |  |  | 1 | crack in PUM in ETMX suspension at LHO while welding
bug 621 waiver | 1 |  | bug 621 waiver | SYS |  |  |  | 1 | LHO ITM03 crack
bug 805 waiver | 1 |  | bug 805 waiver | SYS | 1 |  |  |  | IM3 (HAUX) first structural mode resonance non-compliance