## Electrical cables and fibers
For each IFO:
| Long cable | Length | Part Number | Availability / Procurement | Connector Brackets | Availability / Procurement | Short Cable | Length | Part Number | Availability / Procurement | Other | Availability / Procurement | Routing components | Availability / Procurement
Tip-tilt #1, HAM5 | One D-25 cable | To be checked with Eddie | ? | To be ordered by Rich | One D-25 cable brackets | Matt and Bestsy have none. Janeen looking into it? | One quadrapus | 100" ? | D1000234? | To be checked with Matt H. | 4 B-OSEMS | Betsy checking | cable ties, peek clamps… | ?
Tip-tilt #2, HAM6 | One D-25 cable | 260", from Eddie | ? | To be ordered by Rich | One D-25 cable brackets | See above | One quadrapus | 100" ? | D1000234? | To be checked with Matt H. | 4 B-OSEMS | Betsy checking | cable ties, peek clamps… | ?
Suspension, HAM6 | Two D-25 cables | 260", from Eddie | ? | To be ordered by Rich | Two D-25 cable brackets | See above | Two quadrapus | ? | ? | To be checked with Matt H. | 6 A-OSEMS | 6 available at MIT, need 6 more for the second suspension | cable ties, peek clamps… | ?
Items on VIP, HAM6 | Two D-25 cables | 260", from Eddie | ? | To be ordered by Rich | Two D-25 cable brackets | See above | Two unshielded twisted pairs | ? | ? | To be made. Rich? John? | See section2 of T1700019 | Ordered by John | cable ties, peek clamps… | ?
Beam Diverter, HAM6 | ? | ? | ? | Re-use the existing one | ? | - | ? | ? | ? | - | - | - | cable ties, peek clamps… | ?
| In air fiber | Length | Part Number | Availability / Procurement | Feedthru | Availability / Procurement | In vac fiber | Length | Part Number | Availability / Procurement | Input coupler | Availability / Procurement | Output/collimator | Availability / Procurement
532 nm Pump to OPO | Nufern, 1060 OCT, Acrylate coating, stainless steel jacket | TBD | - | Supplied by MIT | D1600495 | Supplied by MIT | Nufern, 1060 OCT P Polyimide coating, peek braid jacket | TBD | - | Supplied by MIT | Thorlabs Aspheric FiberPorts PAF-X-5-A | Fabrice to order them | Lightpath 355230-FCAPC-532 Customized | John ordered 4 units (1 unit and 1 spare per IFO)
1064 nm Control field/seed to OPO | Nufern, S460HP, Acrylate coating, stainless steel jacket | TBD | - | Supplied by MIT | D1600496 | Supplied by MIT | Nufern, FUD 4194 Polyimide coating, peek braid jacket | TBD | - | Supplied by MIT | Thorlabs Aspheric FiberPorts PAF-X-5-C | Fabrice to order them | Lightpath 355230-FCAPC-1064 Customized | John ordered 4 units (1 unit and 1 spare per IFO)
Control field to fiber switch | Thorlab | 1m? | - | Ordered by MIT | - | - | - | - | - | - | Thorlabs Aspheric FiberPorts PAF-X-5-C | Fabrice to order them | Fiber switch | To be discussed
Seed to fiber switch | P3-980A-FC-1 | 1m? | - | Ordered by MIT | - | - | - | - | - | - | Thorlabs Aspheric FiberPorts PAF-X-5-C | Fabrice to order them | Fiber switch | To be discussed
PSL sample | ? | ? | - | Ordered by MIT | - | - | - | - | - | - | From box? | ? | Lightpath 355230-FCAPC-1064 Standard | John ordered 4 units (need more)
LO to homodyne | P3-980A-FC-1 | 10m? | - | Ordered by MIT | - | - | - | - | - | - | Thorlabs Aspheric FiberPorts PAF-X-5-C | Fabrice to order them | Lightpath 355230-FCAPC-1064 Standard | See above
SQZ LO from PSL | ? | ? | - | Ordered by MIT | - | - | - | - | - | - | From box? | ? | Lightpath 355230-FCAPC-1064 Standard | See above
Fiber switch
Table enclosure interface
Fiber routing (magnets, tray…)
John also ordered: | Lightpath 355230-FCAPC-532 Standard | 4 units for in air testing